## Landingpage > System view
Log in/register: | Person responsible | Development status | Development priority | Notes
The Podcast team member visit our landingpage | Karl | DONE |  | Got to find a name and domain first
Chose to launch / open the webapp | Lukas | Pending
Fill in email as username and password, option tick the box remember me (to not ask for user credentials every time user visit the page) |  | Done ?
Optional user cant remember their password and then click on "forgot password" fill in their email address and we email them a reset password link (when they click on the reset password link we ask for a new password and overwrite the existing one in the database and login the user) |  | Done ?
System check if the user exist, if yes login, if dont exist create new user and send welcome email to the new user. |  | Done ?
Platform:
User is now loged in to the plaform and the system check: if its a team member OR podcast owner. IF its a team member give access to the show he or she is allowed to view. |  | Pending | 10
Sysem check the database for the user, If no podcast has been added before by the user the system ask the user for the podcast name and RSS feed (RSS feed is optional but name is mandatorily) |  | Pending | 10
|  | HOLD for now |  | Här behöver vi skapa default tasks
The user will see all podcasts he/she has access to in the overview and can expand any of them by clicking on them to see the episodes status overview. If its only one pod then auto expand on that pod episode status to minimize clicks for the user
The podcast management platform will automate the guest onboarding and episode workflow as follows:
Guest Invitation and Scheduling:
Guests receive a link to our guest form where they fill in their details (e.g., name, email, bio, and social media links). and in the calendar view select a date and time for the recording.
Episode Creation:
Once the guest submit the form, the system auto-creates an episode in the management portal.
The episode is named %Recording Date% - %guest name% by default (e.g., "2025-01-11 Olle Olsson")
Task Automation:
Clicking on the episode reveals the task list (same task list for every episode but configurable for each episode to chose which tasks they like to include in their workflow from the settings page).
Tasks may include just as an example:
Preparing interview questions.
Sending a confirmation email to the guest.
Create episode cover
Editing and post-production steps.
Drafting promotional materials for social media and newsletters like images shorts and audiograms as examples.
Customization:
The task list and episode details are fully customizable to align with the podcast’s unique requirements.
The platform will manage tasks and episodes as follows:
Task Assignment:
Team members can pick tasks from the episode's task list, by picking a task its assigned to that team member.
Each task has task specific settings, such as deadlines, instructions, and dependencies.
Task Dependencies and Order:
Some tasks are marked as dependent on the completion of others.
The system enforces sequential completion where required, ensuring tasks are completed in the correct order.
The user mark a task as done and based on the task some automatiton might be triggered and/or other tasks might get enabled.
Episode-Specific Task Management:
Each episode maintains its own task list, and the task completion and status is independent of other episodes.
Tasks are standardized across episodes but are uniquely tied to their respective episode.
Completion Tracking:
As tasks are completed, the system updates progress for the episode. example 11/18 tasks done.
When all tasks for an episode are marked complete, the episode is flagged as "Completed."
Team Collaboration:
Team members can collaborate, track task statuses, and view dependencies within the episode's task list.
Notifications or reminders can be sent for overdue tasks or upcoming deadlines.
This structure ensures smooth workflow management, prevents task overlaps between episodes, and enables efficient tracking of episode completion.
Credits
Credits:
1.en random referall kod skapas för en ny användare, som de kan kopiera och skicka eller maila till en vän, dom kan maila till flera vänner (obegränsat) (KLART)
2.Nya användare får 3000 credits (som försvinner efter 30 dagar) (KLART)
3. Användare kan bjuda in vänner via en referral-länk. (KLART)
4.Användare kan bjuda in vänner via en referral-länk. (KLART)
5 Användaren som bjuder in en anna användare via referral länk får credits (200 credits per referral) (KLART) En bonus ges vid uppnådda milstolpar, 1500 bonus credits vid 3 referrals, 1000 credits vid 5, 2500 credits + vip-status. vid 10 (KLART)
6 Credits poäng visas högst upp ( klart)
7. Widget för referral och refferal_bonus milstolpe (KLART) Credits och, referral, referral-bonus uppdateras dynamiskt (alltså automatiskt) både med text och en progress-stapel. (KLART)
8. Pop-up visas om användaren har färre än 500 credits. (Klar) (Kan optimeras så att den inte visas för ofta)
9 (unclaimed credits) 98% klart Knapp visas när användaren har credits att hämta. Exempel: "🎁 You Have 1,500 Unclaimed Credits – Claim Now!" Problem: 🔸 Efter claim visas fortfarande "1500 Unclaimed Credits" tills man refresher sidan. Lösning pågår: Fixa att UI uppdateras korrekt efter claim.
10. Återstående: 🔸 Ska detta göras? Lägg till streak-bonusar för flera referral-inviter inom (en viss tidsram) just nu är den endast baserad på hur många inviter
11 Dashboard Gamification Widget (Main View) (KLAR)
12 Visar användarens nuvarande progress i systemet. Exempel: "You're 2/3 episodes away from unlocking 500 credits!" Episod-progress-stapel fungerar. (behöver kopplas ihop med podavsnitt delen)
13. Daily & Weekly Streak Tracker (Klar)Användare ser sin streak-status i dashboarden. Exempel: "🔥 4-Day Streak – Keep going for an extra 500 credits!" Streak uppdateras dynamiskt.
Återstående: 🔸 Inför visuella streak-ikoner/badges på användarprofiler.
14. Visar topp 3 podcasters baserat på poäng. Exempel: "🏆 Top 3 Podcasters This Week" Dynamisk uppdatering implementerad. One-Click Claim Rewards Button återståede: 🔸 (dock top 3 podcasters är nu hårdkodat måste kopplas ihop meed podcasters) Återstående: 🔸 Lägg till filterfunktioner (t.ex. veckovis, månadsvis, all-time).
15. Sharing & Promotion Strategy ( ej klart eller påbörjat)
16. Where to Introduce the Gamification System? Behöver implementeras: Strategisk placering av gamification-funktioner på olika sidor. Dashboard Banner – "🎯 New Challenges Available – Earn Free Credits!"
17. Ej implementerat: En banner som uppmärksammar användare om nya utmaningar och möjligheter att tjäna credits. Email Notifications – "🔥 You’re Close to Unlocking a New Badge!"
18. Ej implementerat: Automatiska e-postmeddelanden vid milstolpar. Push Notifications – "Only 2 More Episodes to Win a VIP Reward!"
19. Ej implementerat: Notiser till användaren om framsteg. Community Announcements – Launch exclusive challenges in Discord & email.
20.Delning & Marknadsföringsstrategi (⏳ Delvis Implementerat) Mål: Uppmuntra användare att dela och marknadsföra systemet. Status: 🔹 Delvis implementerat Vad är klart? ✅ Användare har en referenslänk och kan tjäna krediter. Återstående: 🔸 Skapa förifyllda sociala medier-delningsknappar (Twitter, LinkedIn, etc.).
21. Ytterligare Gamification-funktioner från Business Model (Ej Implementerade) Efter att ha granskat gamification-dokumentet, här är funktioner som saknas:
22. ❌ Poängsystem Funktionalitet: Användare tjänar poäng separat från krediter. Återstående: 🔸 Implementera en poängbaserad leaderboard för prestationer som inte är kopplade till monetära belöningar.
23❌ Uppdrag & Bounty-system Funktionalitet: Användare kan slutföra speciella uppgifter för extra poäng. Återstående: 🔸 Introducera uppdrag såsom Bug Bounty, Gästfinnare, Referral Streaks
24❌ Tidsbegränsade utmaningar Funktionalitet: Säsongsbaserade evenemang med extra belöningar. Återstående: 🔸 Implementera tidsbegränsade utmaningar med unika belöningar.
25.❌ Streak-bonusar för referral-inviter Funktionalitet: Användare får extra bonus för att bjuda in flera personer inom en kort tidsram. Återstående: 🔸 Skapa streak-bonusar för flera referral-inviter per månad.

## Gamification features
User Flow: Gamification & Points System
1. Points System (Engagement & Competition)
Earning Points: Users gain points by completing tasks, interacting with the platform, and growing their podcast.
Purpose: Encourages competition within teams and across podcasts, driving engagement.
Non-Monetary Value: Points act as an activity and success indicator, not as a currency.
Redemption: Users can exchange points for badges, achievements, and exclusive in-platform rewards.
Leaderboards: Rankings display top-performing users to motivate participation.
First Month Bonus:
New users receive 3,000 points upon joining, which expire after 30 days if unused.
Task-Based Deductions:
Manual tasks → Fewest points deducted.
Automated tasks → More points deducted.
AI-powered tasks → Higher point deduction.
AI+Automation tasks → Maximum point deduction.
Point Retention Strategy: If a user records two episodes per month, their 3,000 points should be nearly depleted by the end of the month, ensuring they either earn or purchase more.
Ways to Earn Points:
Waiting List Referral: Earn 1,000 points for each recruited user.
Task Completion: Each completed task deducts points (not earns them).
Bounties & Missions: Users earn bonus points through structured challenges.
2. Credits System (Paid Platform Access & Premium Features)
Credits = Platform Currency (Used for AI features, automation, and premium tools).
Acquisition:
Monthly allocation (based on subscription plan).
Purchase additional credits on demand.
Earned by contributing to platform growth (e.g., reporting bugs, referrals).
Value: Credits unlock functionalities, unlike points which are for gamification.
Rollover: Unused credits may roll over based on the subscription plan.
Non-Transferable & Non-Monetary Exchange: Credits cannot be exchanged for money or transferred between users.
3. Gamified "Missions" (Bounties & Engagement Challenges)
Each mission is designed to reward user actions that benefit the platform, such as reporting issues, inviting users, or creating content.
Mission Categories:
1. Bug Hunter Mission (Security & Performance Improvements)
Objective: Report platform bugs and issues.
Rewards:
Minor Bug = 50 points
Moderate Bug = 200 points
Critical Bug = 1,000 points
Leaderboard: Top contributors are ranked, and monthly winners get bonus points.
2. Security Guardian Mission (Cybersecurity & API Integrity)
Objective: Identify security vulnerabilities.
Rewards: 500–5,000 points depending on severity.
Exclusive Titles: Earn “Cyber Sentinel” badge for significant contributions.
3. Promoter Mission (Marketing & Growth via Social Media)
Objective: Promote the platform externally.
Rewards:
Social post about platform = 100 points
Blog review = 300 points
Driving 10+ visitors = 1,000 points
Gamification: Earn badges like "Social Influencer" and streak bonuses for consistent promotion.
4. Referral Hero Mission (User & Guest Referrals)
Objective: Invite new users and podcast guests.
Rewards:
New user signup = 200 points
Guest referral = 500 points
If a referred user subscribes = 1,000 points bonus
Leaderboards & Streak Bonuses:
Refer 3 users in 7 days = Extra 500 points
Refer 5 users in a month = VIP badge + 2,000 points
5. Content Creator Mission (Guides, Templates & Tutorials)
Objective: Contribute tutorials, templates, or guides to the community.
Rewards:
Basic submission = 300 points
High-quality, widely adopted content = 1,000 points
Recognition: Featured contributions earn special badges like “Knowledge Sharer”.
6. Engagement Mission (Consistent Platform Usage)
Objective: Actively use the platform's features.
Rewards:
Completing an episode workflow = 100 points
Publishing 3 episodes = 500 points
Using automation = 200 points
Gamification: Streak-based rewards encourage habit-building.
7. Milestone Achiever Mission (Podcast Growth Goals)
Objective: Reach significant platform milestones.
Rewards:
Publish 10 episodes = 1,000 points + "Podcast Pro" badge
Hit 1,000 downloads on an episode = 1,500 points
Bonus Rewards: Unlock discounts or platform perks for major achievements.
8. Feedback Guru Mission (Product Enhancements & Suggestions)
Objective: Provide platform feedback and suggest new features.
Rewards: 200–1,000 points depending on impact.
Gamification: Earn the “Advisor Extraordinaire” badge for significant contributions.
4. Gamification & FOMO Features
To increase engagement, these features create urgency and motivation:
1. Leaderboard Challenges
Rank top users in each category (e.g., Bug Hunter, Promoter, Referral Hero).
Resets monthly/quarterly, with exclusive rewards for top users.
2. Exclusive Badges & Titles
Unlock “Podcast Master,” “Super Referrer,” “Bug Hunter Elite” badges.
Titles appear on user profiles for prestige and recognition.
3. Limited-Time Challenges
Time-sensitive events like:
"Refer 3 users this month → 2,000 points"
"Bug Hunt Week → Double points for all reports!"
4. Point Multipliers
Temporary boosts (e.g., “Earn 2x points on automation features this week!”).
5. Streak Rewards
Incentives for consecutive days/weeks of participation.
Examples:
Login daily for 7 days → Bonus 300 points
Complete 10 tasks this month → 1,000 points
5. Branding & FOMO Strategy
Rebrand Points:
PodTokens, ProCoins, WavePoints, or Creator Credits.
Marketing Phrases:
“Only 5 days left to earn double points on referrals!”
“Don’t miss out on this week’s exclusive challenge!”
“Top 3 bug hunters win a free premium month!”

## Guest form
Description | Type: Information / Action / Outcome
When a new user login for the first time they first get the question popup to say the name of the PodCast and after that is submitted we shold show them a secnd popup that guidethem through the configruration of the the guest form: | Info | The guest form is the collection of information for guests that will apear in the podcast so that the podcast have the personal information as well as social media account details, profile photo and suggested future guests, in the end it also has a date picker functon for the guest to pick a date in the hosts calendar basd on availability.
Click button to request access to google caalendar to view calendar events booked by the guests, Short info box explaining why we need this and what value it give the user | Action
Users need to click 'Allow' on the Google Calendar popup to grant PodManager.AI access | Action | How do we request this do we need to register the company somehow with google for api access
Setup a google calendar appointment page | Action | https://support.google.com/calendar/answer/10729749?hl=en | Can this be automated by us somehow
Instructions for how to create your appointment page | Information Page | Guide page for the user to follow
Submit appointtment page URL to our system so we can send the guests to this page in the guest form step | Action
Verify access by creating test event in calendar and read the test event which should create a new pod episode in pod manager | Action
Appointment page is DONE and Google Calendar access has been GRANTED | System test
The guest form should now be published with a unique URL podmanager.ai/?podcast=theshow | System generated URL
Future optional modifications
Podcast logo to replace the podmanager logo on the guest form
Build our own calendar function and have users share their calendar access for us to block already booked slots in their calendar and only show available slots in the guest form pick a date function
Guest form
Fill out all the text information | PodManager guest form
Upload profile image | PodManager guest form
Proceed button is a submit function that redirect the user to the google calendar appointment page | PodManager guest form
Calendar pick a date view | Google calendar
Submit selected date and time | Google calendar
Confirmation page | Google calendar
Email the guest | System automated action started based on the tasks list

## Complete POD profile form
Complete your pod profile | Action | Type | Feature | Gamified Point (to motivate completion of the profile)
Pod Name | Input field | Form field | User submit info or if info found in db present the existing info | 10
Pod RSS | Input field | Form field | User submit info or if info found in db present the existing info | 10
Pod Logo | Input field | Form field | User submit info or if info found in db present the existing info | 10
Host(s) name(s) | Input field | Form field | User submit info or if info found in db present the existing info | 10
Google Calendar integration | Active/inactive | Button | User click button
Google calenar pick a date URL | Input field | Form field | User submit info or if info found in db present the existing info | 10
Guest form URL | Copy text icon | Text | System generate URL | 100
Podcast Facebook | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast Instagram | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast LinkedIn | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast Twitter | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast TikTok | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast Pinterest | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast Website | Input field | Form field | User submit info or if info found in db present the existing info | 10
Podcast email address | Input field | Form field | User submit info or if info found in db present the existing info | 10
Team | Headline | Headline
Name | Input field | Form field |  | 50 | per invited user
Email | Input field | Form field |  | 50 | per invited user
Role | Drop down | Select one | User/Host | 10 | per invited user
Invite button / Block button | Submit | Button
No delete team member function as we like to keep their profile for the future
Max 5 team members for free account, unlimited for paid account
en pod är en pod en user är antingen en host eller team member en host kan managera podden en team member kan arbeta med tasks i podden

## Create Modify Workflow
The task list configuration page allows podcast owners to create and modify default reusable tasks for each podcast episode. These tasks are automatically applied to every new episode, providing a structured workflow.
Creating a New Task
Accessing the Task Creation Modal:
Clicking "Add New Task" opens a modal with fields to define task details.
Fields and Options:
Name:
Input field for the task name (e.g., "Prepare Interview Questions").
Validation: Required, minimum 2 characters.
Dependent on Other Task Completion:
Option to select none, one or many, task thatt must be done and thus enable dependent tasks to be enabled after a specific task is completed.
Optional: Can be left blank if the task is independent.
Due Time Since Recording Date:
Date picker to specify the due date or duration relative to the recording date.
Options for days/hours after the recording.
Description:
Text area for task instructions or additional details (e.g., "Draft 10 interview questions and share with the host").
Optional field but recommended for clarity.
Action Link:
Text field to provide a link for external resources or tools (e.g., Google Docs template).
Button to add multiple action links if needed.
Action Link Description:
Text field to describe the purpose of the action link (e.g., "Template for questions").
Information Submission Field:
Checkbox to enable a submission requirement for task completion (e.g., uploading a file or submitting a URL).
If checked, the system prompts the assignee to provide this information before marking the task as completed.
Buttons:
Create:
Saves the task and adds it to the default reusable task list.
Validates required fields before submission.
Cancel:
Closes the modal without saving changes.
Modifying an Existing Task
Accessing the Task Modification Modal:
Click on an existing task in the list to open the same modal pre-filled with the task details.
Editing Options:
All fields can be updated:
Rename the task.
Adjust dependencies or due dates.
Update or add action links and descriptions.
Modify the task description or submission field requirement.
Saving Changes:
Clicking "Save" updates the task and reflects changes across all future episodes using the task list.
Does not affect tasks already applied to existing episodes.
UI Features
Dynamic Preview:
Changes are previewed in real-time within the task list.
Reordering Tasks:
Drag-and-drop interface to adjust the sequence of tasks.
Error Handling:
Highlight invalid fields with error messages (e.g., missing name or invalid link).
Field | Input Type | Details
Task Identifier | Auto-generated Text | Unique ID for the task.
Task Name | Text Input | Enter the name of the task (required).
Dependency | Dropdown/Multiselect | Select dependent tasks or none.
Task Type & Action | Dropdown | Choose from: Manual, Automated (Email, System Action, AI Script).
Action Details | Conditional Inputs | Fields for email templates, system triggers, or AI script parameters (shown based on the selected action).
Delay Trigger | Checkbox | Option to add delays for automated actions.
Due Time Since Recording | Date Picker/Duration | Set task deadline relative to recording date.
Task Description | Text Area | Instructions or additional details (optional but recommended).
Save Button | Button | Save the task with the configured details.
Cancel Button | Button | Close the modal without saving.

## Dashboard (Workflow)
Episode | Progress | Cloud Folder | Recording Date | Go-Live Date | Current Task | Actions
Sophia Zhang | ⬛⬛⬜⬜⬜ 40% | Episode Folder | 2025-01-20 | 2025-02-05 | Schedule Social Media Posts (Metricool) | View Open Tasks / Viewing All Tasks
Notes | Consider the background voice in the middle and release as soon as possible
Task Name | Status | Task Type & Action | Assigned To | Due Date/Trigger | Actions
Guest received pitch email to join the show as a guest | ✅ Completed | Automated - Email | Emma | 2025-01-01 | View Details (read-only)
Guest filled out the guest form and picked a date | ✅ Completed | Automated - Form Submitted | Forman | 2025-01-02 | View Details (read-only)
Create episode in the system with predefined tickets | ✅ Completed | Automated - System Action | Ashton | 2025-01-03 | View Details (read-only)
Scheduling confirmation email sent | ✅ Completed | Automated - Email | Emma | 2025-01-04 | View Details (read-only)
Guest preparation email sent | ✅ Completed | Automated - Email | Emma | 2025-01-05 | View Details (read-only)
Create cover art | ✅ Completed | Manual - Team Member Action | Alice | 2025-01-06 | View Details (read-only)
Email sent to guest with cover art and suggestion to post in social media | ✅ Completed | Automated - Email | Emma | 2025-01-07 | View Details (read-only)
Recording Scheduled | ✅ Completed | Automated - System Action | Ashton | 2025-01-09 | View Details (read-only)
Schedule Social Media Posts (Metricool) | 🔄 In Progress | Manual - Team Member Action | Karl Lillrud | 2025-02-01 | View Details
Generate shorts with OPUS | 🟩 Ready to Start | Manual - Team Member Action | Unassigned | Ready to Start | Assign to Me
Produce quote images | 🟩 Ready to Start | Manual - Team Member Action | Unassigned | Ready to Start | Assign to Me
Guest follow-up ask for recommendations | ⏳ Awaiting Dependency | Automated - Email | Emma | 2025-02-02 | View Details
Episode | Progress | Cloud Folder | Recording Date | Go-Live Date | Current Task | Actions
Sophia Zhang | ⬛⬛⬜⬜⬜ 40% | Episode Folder | 2025-01-20 | 2025-02-05 | Schedule Social Media Posts (Metricool) | Viewing Open Tasks / View All Tasks
Notes | Consider the background voice in the middle and release as soon as possible
Task Name | Status | Task Type & Action | Assigned To | Due Date/Trigger | Actions
Schedule Social Media Posts (Metricool) | 🔄 In Progress | Manual - Team Member Action | Karl Lillrud | 2025-02-01 | View Details
Generate shorts with OPUS | 🟩 Ready to Start | Manual - Team Member Action | Unassigned | Ready to Start | Assign to Me
Produce quote images | 🟩 Ready to Start | Manual - Team Member Action | Unassigned | Ready to Start | Assign to Me
Guest follow-up ask for recommendations | ⏳ Awaiting Dependency | Automated - Email | Emma | 2025-02-02 | View Details
[7 empty] | 2025-01-17 | View Details (read-only)
[7 empty] | 2025-01-18 | View Details (read-only)
[7 empty] | 2025-01-18 | View Details (read-only)

## WORKFLOW Task List
Developed by | Order to do the tasks | Identifier | Task | Dependency | Action type | Task Type Selector | Action | Points | AI team member name | Explanation | Trigger/Delay | Submission requirement | Future improvement | Task action link 1 | Task action link 2 | Integration documentation
? | TOP Prio | Task 001 | Guest received pitch email to join the show as a guest | No dependency | Checkmark | Automated | Email | 20 | Emma
någon | TOP Prio | Task 002 | Guest filled out the guest form and picked a date | Previus step | Checkmark | Automated marked as done when submitted | Form submitted | 20 | Forman | Done manually by the guest | CRM details saved and date for recording saved
Daniel? | TOP Prio | Task 003 | Create episode in the system with all predefined tasks | Task 001 | Checkmark | Automated | System action | 40 | Ashton | Automatically identified from guest form | Run daily at 8:00
Sebastian, Tim, Frank | TOP Prio | Task 004 | Scheduling confirmation email sent to the guest | Task 001 | Checkmark | Automated | Email | 20 | Emma |  | Sent same date as form is registered by the guest
Sebastian, Tim, Frank | TOP Prio | Task 005 | Preparation details for the recording sent by email to the guest | Previus step | Checkmark | Automated | Email | 20 | Emma | Pre-recording checklist (chrome update, silent space). | Sent one week before the recording date
| TOP Prio | Task 006 | Create cover art | Task 003 + delay trigger | Upoload action, Link button for resources | Manual | Team member | 60 |  | Use the uploaded profile photo and design cover art in Figma | Save cloud drive link | file upload and verification system as part of the task submission requirements​. |  | Link to cloud drive where images are saved | Link to audio cover
Sebastian, Tim, Frank | TOP Prio | Task 007 | Email sent to guest with cover art and suggestion to post in social media | Previus step | Checkmark | Automated | Email | 20 | Emma |  | Run daily at 8:00
Jeeno, Robin | TOP Prio | Task 008 | Guest OSIN GPT used to find out more about the guest | Task 003 | Checkmark | Automated | AI Script | 40 | Eli | Saved in the CRM
Jeeno, Robin | TOP Prio | Task 108 | Generate Guest intro and outro "Hi, I am NAME NAME and im your host. In todays episode we have XXX who have done xyz and achieved xyz bla bla bla" using the OSIN data and using elevenlabs voice API or Synthesia video avatars. OUTRO: I hope you enjoyed todays episode, some key things to bring with you from this episode is X Y Z. Be sure to follow the show in social media and in your podcast app. | Task 008 | Checkmark | Automated | AI Script |  |  | We use the osin data and promt out a short guest pitch which we then send to eleven labs or synthesia to generate the audio or video | Run as soon as we have the OSIN data saved
behöver vi denna | TOP Prio | Task 009 | Recording Scheduled | Task 002 | Checkmark | Automated | System action | 20 | Ashton | Verify calendar event is created and the 'Recording date' column in status doc is updated
Sebastian, Tim, Frank | TOP Prio | Task 010 | Email sent to guest with joining link x minutes before the scheduled recording session | Task 002 + delay trigger | Checkmark | Automated | Email | 20 | Emma |  | Send 1 hour before recording starts
Berkay och Balowni | TOP Prio | Task 011 | Recording the episode | No dependency | Checkmark | Manual | Host records | 60 |  | Record with Riverside.fm (check mic, lighting, environment) |  |  | Riverside, Studio or other setup
Peter | TOP Prio | Task 111 | Upload the raw audio and/or video file to PodManager | Task 011 | Upoload action, Link button for resources | Manual | Team member | 100 |  | This is the cut and edit autopilot feature where we auto edit the recording to make it more focused | Save cloud drive link |  | Auto access using API calls
Peter | TOP Prio | Task 012 | Check the transcript and make corrections | Previus step | Checkmark | Manual | Team member | 60 |  | Especially names often is transcribed incorrectly
Peter | TOP Prio | Task 013 | Transcript saved to the episode database | Previus step | Upoload action, Link button for resources | Manual | Team member | 60 |  |  |  |  | Sould be possible to automate using scraping or webhooks
Peter | TOP Prio | Task 014 | AI episode auto editor - Suggestt exact parts to remove which would improve the episode | Previus step | Checkmark | Automated | AI Script | 40 | Alan | Run the transcript through our GPT https://docs.google.com/document/d/1BAg-MHN6RldfTl81z3xi6oYDisJ3a2SpoVPTwMCW3y0/edit?tab=t.0
Peter | TOP Prio | Task 015 | Auto cut and edit the recording by removing parts in the script | Previus step | Checkmark | Manual | Team member | 60 |  | Work based on your personal opinion in combination with the improvementt suggestions given to you by our GPT
Peter | TOP Prio | Task 016 | This is now done by the auto pilot feature: Extract the final transcript from Riveside and Save to the episode database and overwrite the previous script | Previus step | Upoload action, Link button for resources | Manual | Team member | 60 |  |  |  |  | Sould be possible to automate using scraping or webhooks
Jeffry | Low prio | Task 017 | Responds with type of background music and sound efffects that may improve the emoional impact of the episode | Previus step | Checkmark | Automated | AI Script | 40 | Simon | Run the transcript through our GPT https://docs.google.com/document/d/1IiuGb493nrXWAItRjhaiVKX5RlgqNZkfzS0lCK1xUAw/edit?tab=t.0 use this document for further feature ideas: https://docs.google.com/document/d/10g242WYWIbr9gQnAyHkNX6e4uN_A3A-Fq_KqkCe0Gc8/edit?tab=t.0#heading=h.972oebwgpuzt
Jeffry | Low prio | Task 018 | Implementt the background sound suggesttions where they add value to the episode | Previus step | Checkmark | Manual | Team member | 60 |  | Work based on your personal opinion in combination with the improvementt suggestions given to you by our GPT
| Low prio | Task 019 | Riverside specific editing steps | Previus step | Multiple checkmarks per action you want to do in Riverside | Manual | Team member | 60 |  | Add intro/outro clips, smooth speech, generate magic clips
Peter | Medium Prio | Task 020 | Improve audio (Final step for Riveside episode to be completed) | Previus step | Multiple checkmarks per action you want to do in Riverside | Manual | Team member | 60 |  |  |  |  | Sould be possible to automate using webhooks or macro
Balowni | TOP Prio | Task 120 | Release date decided | Previus step | Imput date selector field |  |  | 40
Attapon och Kristofer | Low prio | Task 021 | Generate shorts with OPUS using OPUS API | Previus step | Checkmark | Manual | Team member | 40 |  | Create and upload short-form content |  |  | Sould be possible to automate using webhooks or macro |  |  | https://help.opus.pro/api-reference/overview
Attapon och Kristofer | Low prio | Task 022 | Shorts saved to cloud drive | Previus step | Upoload action, Link button for resources | Manual | Team member | 40 |  | Run the transcript through Quote GPT | Save cloud drive link |  | Sould be possible to automate using webhooks or macro
| Medium Prio | Task 023 | Generate quotes | Task 016 | Checkmark | Automated | AI Script | 40 | Alice
| Medium Prio | Task 024 | Produce quote imags | Previus step | Checkmark | Manual | Team member | 40
| Medium Prio | Task 025 | Save quote images to cloud drive | Previus step | Upoload action, Link button for resources | Manual | Team member | 20 |  |  | Save cloud drive link
Linna | TOP Prio | Task 026 | Send Email with link to download shorts and quote images to the guest | Task 022 and Task 025 | Checkmark | Automated | Email | 20 | Emma |  | when cloud drive link exist
Alexis | TOP Prio | Task 027 | Guest follow-up ask for recommendations of other guests | Task 011 + delay trigger | Checkmark | Automated | Email | 60 | Emma |  | 14 days after he episode is live
| Low prio | Task 028 | Upload and Schedule podcast release | Task 020 | Checkmark | Manual | Team member | 60 |  |  |  |  | Sould be possible to automate using webhooks or macro
| Low prio | Task 029 | Upload and Schedule video pod release | Task 120 | Checkmark | Manual | Team member | 60 |  |  |  |  | Sould be possible to automate using webhooks or macro
| Low prio | Task 030 | Schedule live streaming of the episode | Task 120 | Checkmark | Manual | Team member | 40 |  | Plan live-stream replay if required |  |  | Sould be possible to automate using webhooks or macro
| Low prio | Task 031 | Schedule Social Media Posts (Metricool) | Task 025 | Checkmark, Link button for resources | Manual | Team member | 40 |  | Schedule posts with guest tagging using @menion |  |  | Sould be possible to automate using webhooks or macro
| Low prio | Task 032 | Generate FAQ | Task 016 | Checkmark | Automated | AI Script | 60 | Adrian | Run the transcript through FAQ GPT
| TOP Prio | Task 033 | Review and approve as OK to publish | Task 120 and 029 and 030 and 031 | Upoload action, Link button for resources | Manual | Team member | 40 |  |  |  |  | Should be possible to automate for manuall aproval
| Low prio | Task 034 | Generate blog post on LinkedIn | Task 016 | Checkmark | Automated | AI Script | 60 | Isaac | Run the transcript through Blog post GPT
| Low prio | Task 035 | Review and combine with the FAQ and publish on Linkedin and Squarespace website and Medium.com | Previus step | Checkmark, Link button for resources | Manual | Team member | 40 |  |  |  |  | Should be possible to automate for manuall aproval
Jeeno robin | Low prio | Task 036 | Generate full episode page on the podcasts landingpage as an episode subpage with transcript FAQ, learnings from the episode, shorts and guest details | Task 016 | Checkmark | Automated | AI Script | 60 | Ava | Publish the full transcript with speaker (Karl Lillrud speaking:) call outs
| Low prio | Task 037 | Review and publish on website | Previus step | Checkmark, Link button for resources | Manual | Team member | 20 |  |  |  |  | Should be possible to automate for manuall aproval
| TOP Prio | Task 038 | “Episode goes live soon” or “Now live” announcement | Task 120 + delay trigger | Checkmark | Automated | Email | 40 | Emma
| Medium Prio | Task 042 | Newsletter GPT | Task 016 | Checkmark | Automated | AI Script | 40 |  | Run the transcript through our GPT https://docs.google.com/document/d/1BAg-MHN6RldfTl81z3xi6oYDisJ3a2SpoVPTwMCW3y0/edit?tab=t.0
| Low prio | Task 040 | Host improvement feedback GPT | Task 016 | Checkmark | Automated | AI Script | 20 | Erik | Run the transcript through our GPT https://docs.google.com/document/d/1dbeeGGWZb-ldvJfNCgxZjGarb2FezvqaCBZvFPTqd7g/edit?tab=t.0
Berkay | TOP Prio | Task 039 | Mark episode as completed | All tasks marked as done will auto mark his as done | Checkmark | Automated | System action |  | Ashton | Confirm all tasks are marked as done
Task 043
Task 044
Task 045
Task 046
Task 047
Technical solutions:
|  |  |  | Some tasks (e.g., "Generate FAQ") are highly reusable across episodes but require specific templates or AI configurations. The user flow does not address how these templates can be pre-configured and referenced. |  | Solution: Introduce a task template repository with AI configuration parameters that can be linked during task creation​​.
|  |  |  | Automated notifications (e.g., notifying editors post-recording) are mentioned but not integrated as part of task logic. |  | Solution: Extend the task system to include dynamic triggers for email or notification dispatch based on task status​​.
THE BLUE MARKED LINES ARE MIGRATED TO GITHUB, ASIGN YOUR ROLES THERE

## Dashboard (General info)
Badge | Profile | Tasks Completed This Month | Total Points | Months Won | Shadow Goal Currentt/Previous month
🥇 | Sophia Zhang | 12 | 5200 | 3 | 15 / 12
🥈 | Karl Lillrud | 10 | 4800 | 5 | 15 / 11
🥉 | Emma Watson | 15 | 4500 | 6 | 15 / 12
⚪ | Simon Walker | 8 | 3200 | 2 | 10 / 12
⚪ | Alice Lee | 9 | 2500 | 4 | 9 / 12
Information:
This is view that that is dynamically updatated in the dashboard to show the progress of the team and to make the work into a competition.
Users gain points for each task completed
Badges
Purpose: Recognizes user achievements with tiered visual markers based on total points.
Levels:
🥇 Gold (Top Performer)
🥈 Silver (High Achiever)
🥉 Bronze (Active Contributor)
⚪ Clear (New or Low Activity)
Logic: Automatically updates based on the user's Total Points.
Profile
Purpose: Identifies the team member by name.
Tasks Completed current month
Purpose: Tracks the number of tasks completed by the user in the current month.
Usage: Provides a clear snapshot of monthly productivity.
Logic: Updates dynamically as tasks are completed.
Total Points
Purpose: Reflects cumulative points earned by the user based on task completion.
Logic:
Points are earned from tasks, challenges, and missions (as per the gamification model).
Automated calculations
Months Won
Purpose: Displays the number of months the user has achieved the highest task completion or points score among team members.
Usage: Encourages consistent performance over time.
Shadow Goal
Purpose: Shows the user's current task completion versus their performance during the same period last month.
Format: Current Month Tasks / Previous Month Tasks
Example: 15 / 12 indicates 15 tasks completed this month versus 12 tasks completed at the same point last month.
Logic: Encourages self-competition and progress by comparing performance over time.
How It Works
Dynamic Updates:
The leaderboard updates in real-time as users complete tasks and earn points.
Shadow goals adjust dynamically based on the current and previous month's data.
Engagement Features:
Badges motivate users to improve their rank.
Shadow goals allow users to chase personal improvement without direct competition.
Developer Notes:
Data Source: Fetch task and points data from the user activity database.
Badges: Use conditional formatting to determine badge icons based on point thresholds.
Shadow Goals: Compare the current month's task data with the equivalent time range from the previous month.
Leaderboard Reset: Reset points and tasks completed at the start of each month but retain historical data for months won and shadow goal tracking.
User Benefits
Transparency: Users can see exactly where they stand compared to others.
Motivation: Compete with teammates or strive to beat personal bests.
Clarity: Easy-to-read interface with actionable metrics and real-time updates.

## Team page
Team Member List (Table Format):
Displays team members in a clean, sortable table with the following columns:
Name: Full name of the team member.
Role: Role assigned to the member (e.g., Admin, Editor, Team Member).
Email: Clickable email address for direct communication.
Phone Number: Optional contact number, if provided.
Tasks Assigned: A count of tasks currently assigned (e.g., "5 tasks").
Status: Active or inactive status.
Actions (last column):
Edit Role: Button/icon to update the member's role.
Disable: Button/icon to Disable the member from the team.
View Tasks: Button/icon to see a detailed breakdown of the member’s tasks.
Search and Filter:
Search Bar: Search for a team member by name, email, or role.
Filters:
By Role: Admin, Editor, Team Member.
By Status: Active, Inactive.
By Task Count: Members with most or least tasks assigned
Team Member Details (Expandable Row or Modal):
Clicking on a team member’s row opens additional details:
Profile Picture (if uploaded).
Assigned Episodes: Lists the episodes they are contributing to.
Task Details: Displays tasks with deadlines, completion status, and dependencies.
Contact Information: Includes email, phone number, and optional links to social media profiles.
Add New Team Member:
Button to add new team members:
Opens a modal where the owner can input the new member's email, assign a role, and send an invitation.
Option to pre-assign tasks or access levels during the invitation process.
Notifications and Collaboration Features:
Notifications: Highlights overdue tasks or pending actions for team members.
Team Messaging: Quick links to email or chat directly with team members.
UI Features
Visual Indicators:
Icons for roles (e.g., shield for Admin, pencil for Editor).
Color-coded task statuses (e.g., green for completed, red for overdue).
Responsive Design:
Fully responsive for desktop, tablet, and mobile views.
Real-Time Updates:
Reflects changes instantly when tasks, roles, or member details are updated.

## CRM Guests view
The Guests View in the CRM provides a centralized interface for managing guest profiles, tracking their activity, and streamlining communication. It offers a variety of tools to understand guest backgrounds, coordinate interactions, and analyze their engagement with podcast episodes.
Guest Profile Overview
Guest Details:
Name:
Full name of the guest.
Editable field for corrections.
Biography:
Brief bio summarizing the guest’s background, expertise, and relevance to the podcast.
Example: "Author and keynote speaker specializing in AI innovation."
Tags:
Customizable tags for categorizing guests (e.g., "Tech Innovator," "Entrepreneur," "Author").
Used for filtering and segmentation.
Areas of Interest:
Topics or themes the guest is passionate about (e.g., "AI," "Leadership," "Sustainability").
Helps match them with relevant podcast topics.
Contact Information:
Email:
Clickable email address for direct communication.
Integrated with email services for sending and tracking messages.
Social Media Links:
Links to public profiles (e.g., LinkedIn, Twitter).
Allows for quick background checks or outreach.
Activity and Engagement Tracking
Public Information Retrieval:
LinkedIn Web Scraping:
Automatically fetches and updates public details like current role, company, and expertise.
Engagement Insights:
Identifies if the guest posts about their podcast episode.
Tracks engagement rates on those posts (e.g., likes, comments, shares).
Communication Status: | Karl sa att jag skulle ta bort dessa tills vidare
Tracks the status of interactions with the guest:
Pending: Awaiting initial response or confirmation.
Scheduled: Guest confirmed for a recording date.
Completed: Episode recorded and published.
Performance Metrics:
Monitors guest-related outcomes:
Post-episode engagement (e.g., how much traffic their episode generated).
Social media impact (engagement rate on posts promoting the episode).
Email Integration
Send and Receive Emails:
Integrated email tools for communication directly within the CRM.
Pre-written templates for invitations, confirmations, and follow-ups.
Email Tracking:
Tracks open rates, link clicks, and replies for sent emails.
Displays a history of all communications with the guest.
Automated Reminders:
Sends reminders for incomplete tasks (e.g., guest form submissions) or upcoming deadlines.
Filters and Segmentation
Filter Options:
Tags:
Filter by guest categories or topics of expertise.
Segments:
Group guests based on demographics, industries, or prior collaboration status.
Communication Status:
Filter by pending, scheduled, or completed communication.
Performance Metrics:
Filter by engagement rate, social media activity, or episode performance.
Search Functionality:
Search guests by name, tags, areas of interest, or email.
Actions and Features
Guest Management Actions:
Add New Guest:
Form to create a new guest profile with required and optional fields.
Edit Guest Profile:
Update bio, tags, or contact information.
Remove Guest:
Archive guest profiles no longer in use (with confirmation).
Engagement Tracking Automation:
Automatically detect and log social media activity related to the podcast episode.
Export Data:
Export guest lists with filters applied (e.g., "All tech experts who posted about their episode").
UI Features
Dynamic Layout:
Grid or list view with profile pictures for visual identification.
Visual Indicators:
Status badges for communication (e.g., Pending, Scheduled, Completed).
Real-Time Updates:
Automatically refreshes engagement metrics and communication logs.

## Settings page
User Account Settings
A. Personal Information
Team members can update their full name, email address, and profile picture.
Form Elements:
Full Name: Text input, required, 2–50 characters.
Email Address: Email input, required, unique, follows email format.
Profile Picture: File upload (JPG, PNG, GIF, max 5MB), optional, with preview.
B. Password Management
Team members can change their account password.
Form Elements:
Current Password: Password input, required, matches existing password.
New Password: Password input, required, 8+ characters with complexity rules.
Confirm New Password: Password input, required, matches New Password.
UI Features:
Password strength meter.
Toggle visibility for password inputs.
E. Security Settings
Team members can enable Two-Factor Authentication (2FA) for added security.
Form Elements:
Toggle to enable/disable 2FA.
Options: SMS or authenticator app.
UI Features:
Clear setup instructions with QR codes or manual entry for authenticator apps.
Recovery options for lost 2FA access.
Settings for Podcast Owners | Finns men behöver delas till Podcast Owners och guest
Podcast owners have access to manage all podcast-related details, in addition to their personal account settings.
1. Account Settings
Same as team members (see above).
2. Podcast Management
A. Podcast Details
Podcast owners can update their podcast's name, RSS feed, and other core details.
Form Elements:
Podcast Name: Text input, required, 2–50 characters.
RSS Feed: URL input, optional, must follow URL format.
UI Features:
Clear instructions for adding or editing podcast details.
Validation to ensure RSS feed is correctly formatted.
B. Guest Management
Owners manage guest-related settings for their podcast.
Form Elements:
Links to invite guests or update guest forms (name, email, social links).
UI Features:
Real-time notifications when guest forms are submitted.
Overview of pending and completed guest forms.
C. Task Management
Owners control task workflows and assign tasks to team members.
Form Elements:
Configurable task lists for each episode.
Fields to update task dependencies, deadlines, and assignments.
UI Features:
Drag-and-drop task arrangement.
Visual dependency mapping to enforce task order.
D. Integration Settings
Owners set up and manage integrations for their podcast.
Form Elements:
Email, calendar, and LinkedIn integrations.
Fields for API keys, OAuth authentication, and toggle options.
UI Features:
Real-time sync status for calendar and email services.
Secure storage for API credentials.
E. Billing and Subscription
Owners manage billing details and subscription plans.
Form Elements:
Payment methods (add, update, or remove).
Subscription plan selection and management.
UI Features:
Plan comparison charts.
Clear billing history with download options for invoices.
F. Permissions and Roles
Owners manage team member access to podcast features.
Form Elements:
Role assignments (e.g., Admin, Editor, Team Member).
Permissions matrix for feature access.
UI Features:
Real-time role updates.
Bulk role assignment and detailed permission descriptions.

## Welcome page
Step into the future where time is returned to you! | Welcome to your new reality of more time and less stress!
As our community grows faster than anticipated, we've started waitlisting new registrations to preserve the quality of service. | As we navigate an unprecedented volume of sign-ups, we've implemented a waitlist for new registrations to ensure quality service for everyone.
Get prioritized in the queue by inviting a friend to join the waitlist, and receive 1,000 extra credits in your account as soon as you're both onboarded! | Fast-track your access! Refer a friend to join the waitlist, and we'll thank you both with 1,000 credits once you're active users.
Thank you for waiting - We'll let you know as soon as you're in! | Thank you for waiting

## FUTURE Sponsor and advertisers
Manage
inegrate
Offer
mattch brands with pods

## FUTURE FEATURE Date Picker
Explanation | Action | Type | Result | Example
API Integration to read users calendar to find available slot |  | API Integration
Default slot time in minutes | Type value | Number field |  | 90 min
Default days available | Multi select | Tick boxes
Name
Email
Submit
Automation script 24 hours before appointment
Subject: Confirmation request: Ready for Tomorrow?
Hi %GuestName%,
Just a quick reminder that tomorrow at this time, you'll be joining %HostName% to record an episode for %PODName%!
We know you're busy, and things can come up in last minute. To make sure no time is lost, please just hit the button below to confirm you're good to go:
[Confirm Recording Attendance]
If we don’t get a confirmation, the system will automatically reschedule the recording for the same time next week—just to keep things smooth and stress-free.
Looking forward to it!
Best,
%YourName%

## FUTURE Landingpage
New user
Head witth clear value
Info
As seen in
What people say
AI
Features
Pricing
Footer

## FUTURE Global guests view
A view where guests can chose to be guests on other shows

## FUTURE Guest system check
Requirement | Can it be Built Automatically? | Explanation | No (Browser Settings Cannot Be Manipulated)
1. Validate that the user's web browser is up to date with the latest version of Google Chrome or Edge | Yes | Solution: Utilize JavaScript to detect the browser type and version via the navigator.userAgent property. Compare the detected version against the latest version fetched from the official browser APIs or websites. If outdated, prompt the user to update. | Can it be Built Automatically with User Permissions?
2. Validate that the user has a minimum of 5 GB free space on his or her computer | No | Explanation: Cannot be Done Automatically. Web browsers restrict access to detailed system information for security and privacy reasons. Therefore, detecting free disk space is not feasible through standard web technologies. | Yes
3. Check camera and audio for light and quality | Partially | Solution: Use the getUserMedia API to access the camera and microphone. Analyze the video stream to assess lighting conditions using image processing techniques (e.g., checking brightness levels). For audio quality, analyze the audio stream for clarity and background noise. However, comprehensive quality assessment may require advanced algorithms and user permissions. | Partially (Requires Additional Software)
4. Check internet speed | Yes | Solution: Implement a speed test by measuring the time taken to download and upload specific resources. Utilize JavaScript to perform these measurements and calculate metrics like download speed, upload speed, and latency. Libraries like speedtest.net's API can be integrated for more accurate results. | Yes (With User Consent) | Ensure a stable internet connection. (Wired connection is highly recommended) You can test it here.
5. Validate computer plugged into power outlet | No | Explanation: Cannot be Done Automatically. Web browsers do not have access to system-level power status information due to security and privacy constraints. | Yes
6. Get transported to the recording studio link | Yes | Solution: Implement a redirect using JavaScript's window.location or HTML <a> tags to navigate the user to the specified recording studio link. Ensure that the link is secure (HTTPS) and consider opening it in a new tab if appropriate. | Partially (Requires Additional Software)
7. Turn off any VPNs, browser extensions, firewalls, or content blockers | No | Explanation: Cannot be Done Automatically. Detecting or controlling VPNs, browser extensions, firewalls, or content blockers is beyond the scope of standard web technologies. Browsers isolate these components to protect user privacy and security. | Yes
8. Enable graphics acceleration if using a browser | No | Explanation: Cannot be Done Automatically. Enabling or disabling graphics acceleration is a browser setting that cannot be manipulated via web pages. Users must manually adjust these settings within their browser preferences. | No (Due to Security Restrictions)

## FUTURE POD Award
Award Program Structure
Name of the Award:
"PodManager Podcast Excellence Awards" | number of interviews | number of social reach | spead of team | numberr of recordings
Tagline: Recognizing Podcasts that Inspire, Engage, and Lead.
Nomination Process:
Open Call for Entries: Invite all podcasters to nominate themselves or be nominated by others.
Platform-Exclusive Requirement:
To qualify, podcasts must create an account and actively use PodManager.AI for at least 30 days during the nomination phase.
During this time, all podcast-related metrics are automatically tracked and assessed.
Qualification Criteria
Podcasts qualify for the award by meeting the following measurable benchmarks tracked exclusively through PodManager.AI:
Number of Interviews:
Tracks the total number of guest interviews conducted within the usage period.
Highlights podcasts that demonstrate collaboration and effort in building a network of quality guests.
Benefits of using PodManager.AI:
Simplifies guest management with a built-in CRM to track communication.
Automates follow-ups and organizes booking schedules seamlessly.
Social Media Reach:
Evaluates the podcast’s impact on social media platforms by analyzing:
Growth in follower count.
Engagement metrics such as likes, shares, and comments.
Integration with PodManager.AI for automated post scheduling and tracking.
Shows how podcasts are leveraging social platforms to grow their audience.
Team Speed and Efficiency:
Measures how effectively the podcast team collaborates using PodManager.AI tools.
Metrics include:
Task completion rates and deadlines met.
Workflow speed in production cycles (e.g., editing, promotion).
Use of shared calendars, task boards, and automated reminders.
Emphasizes the importance of streamlined teamwork for producing high-quality episodes.
Episode Frequency:
Tracks how consistently podcasts record and release new episodes.
Benefits of using PodManager.AI:
Scheduling reminders, automated publishing workflows, and clear production timelines.
Awards consistency and commitment to content creation, which are key indicators of audience loyalty and podcast growth.
Engagement Growth:
Captures growth in listenership and overall engagement.
Metrics include:
Audience retention rates over time.
Number of listens/downloads (if tracked via integrated analytics).
Listener feedback, ratings, and reviews.
Shows how well the podcast connects with its audience.
4. Award Categories
Best Podcast Team Collaboration:
Awarded to the podcast team with the most efficient and productive workflow.
Recognizes the effective use of PodManager.AI’s team collaboration tools, such as task management, calendar integration, and automated workflows.
Top Social Media Impact:
Honors podcasts that demonstrate outstanding social media growth and audience engagement.
Data-driven insights from PodManager.AI reveal the podcast’s reach and influence on platforms like Instagram, Twitter, and TikTok.
Most Prolific Podcast Creator:
Celebrates the podcast with the most consistent episode output during the evaluation period.
Tracks both quantity and regularity of new releases, rewarding podcasters who maintain a steady publishing schedule.
Best Guest Collaborator:
Recognizes podcasts that excel at booking, managing, and hosting diverse guests.
PodManager.AI tracks the number of guest interviews and their quality based on engagement and guest prominence.
Audience Favorite:
Based on user voting or audience engagement metrics.
Gives listeners a chance to have a say in the awards, encouraging podcasters to promote their participation and drive traffic to the platform.
5. Key Benefits to Participants
Public Recognition:
Winners and finalists receive digital badges and certifications (e.g., “Winner of PodManager Podcast Excellence Awards”).
These badges can be displayed on websites, social media profiles, and promotional materials, enhancing credibility.
Marketing Exposure:
Featured on PodManager.AI’s official website, newsletters, and social media channels.
Winners’ success stories and metrics published as case studies to highlight how they excelled using the platform.
Opportunity to be interviewed or featured in special PodManager.AI content, such as blog posts or webinars.
Access to Premium Features:
All nominees receive a free trial of PodManager.AI premium tools for one month.
Exclusive discounts for all finalists and winners to incentivize long-term use of the platform.
6. Promotion Strategy
Teasers and Announcements:
Use targeted social media ads and email campaigns to build excitement for the awards.
Create content such as short videos, infographics, and testimonials from past winners to showcase the awards’ credibility.
Partnerships:
Collaborate with podcast directories (e.g., Spotify, Apple Podcasts) and influencers to amplify visibility.
Partner with podcasting conferences or communities to promote the awards.
User Onboarding Funnel:
Tailor onboarding specifically for award participants, with guides on:
How to use PodManager.AI to track metrics that will contribute to their nomination.
Tutorials for maximizing tools like guest CRM, task boards, and analytics.
Send personalized progress updates to participants throughout the evaluation period, showing their performance against benchmarks.
7. Timeline
Announcement Phase (Month 1):
Launch the awards with an email blast, social media posts, and a dedicated landing page.
Encourage immediate signups with early bird perks, like extended trial periods or special resources.
Usage Period (Months 2–3):
Participants must use PodManager.AI tools to generate metrics for evaluation.
Weekly emails or in-app notifications remind users to stay active and update their progress.
Evaluation Phase (Month 4):
The PodManager.AI team analyzes participant data and selects finalists based on performance metrics.
Award Ceremony (Month 5):
Host a live-streamed award ceremony to announce winners and showcase their achievements.
Include guest speakers or industry experts to add credibility to the event.
8. Execution Plan
Award Landing Page:
Design a visually engaging page outlining:
Award categories, timelines, and qualification criteria.
Steps to sign up and participate.
Real-time progress tracker for nominees (linked to PodManager.AI metrics).
Automated Tracking and Updates:
Use PodManager.AI’s automated workflows to track participants’ progress in real-time.
Send personalized emails with updates like:
“You’ve completed 75% of tasks needed to qualify for the Best Team Collaboration award!”
Award Dashboard for Participants:
Build an intuitive dashboard where nominees can:
View their current metrics and standings.
Get tips on how to improve performance (e.g., scheduling more interviews or optimizing workflows).
9. Follow-Up
Convert Participants into Long-Term Users:
Offer personalized consultations for finalists, showing them how PodManager.AI can further optimize their podcasting efforts.
Provide exclusive discounts on premium plans for all participants.
Showcase Success Stories:
Publish detailed stories of winners and how PodManager.AI helped them achieve success.
Use these stories in marketing to attract more users.
Plan for Next Year:
Use feedback from participants to refine the awards.
Start promoting next year’s awards immediately to maintain momentum.

## FUTURE Feature
Analyse episodes and give a idea list of future episode topics based on previous theme transcript and what was most interesting from listeners based on statistics
Future feature idea: jag tror att den github lösning som jag snubblade på som samlar in info om poddar kommer ge oss en ganska bra databas med sisådär 4 miljoner poddar om chat gpt har rätt i sitt antagande om hur många aktiva poddar det finns. | med den databasen på plats kanvi ju vid tillfället att en användare registrerar sig automatiskt kolla i vår databas om den mailadressen är känd av oss i koppling till vår enorma dtaabas över poddar och när hen registrerar sig säga typ HEJ är det du som gör podden XYZ ja / nej, ja då har vi redan hans RSS feed från vår databas så hen slipper fylla i den infon i registreringen, ser ju snyggt ut att vi har koll., svarar hen nej så kör vi på enligt hur det fungerar idag där de får fylla i sin rss feed url själva
Episode completion approval | for clients or guests to approve before episode is published
copy features for guests matching from https://www.matchmaker.fm/